Process for Developing IEP

| When |  | What | Who |
| --- | --- | --- | --- |
| 6 weeks prior to meeting PLANNING PHASE |  | Schedule IEP meeting - inform all team members of date/time | Case Manager (CM) with each IEP team member |
|  |  | - ask for preferences on how team will communicate during planning phase (e.g. via student, mail, email, planning conference, etc.) |  |
|  |  | - get written consent if information is to be shared electronically |  |
|  |  | Confirm attendance | Each team member with CM |
|  |  | Determine who will support the student in preparing and planning for the IEP meeting | CM and IEP team members |
|  |  | Determine what information gathering materials will be used (e.g. forms from It’s About Me or others agreed to by IEP team) | CM in consultation with IEP team members |
|  |  | Send information package to all team members forms for gathering information - General information (strengths, concerns, needs interests, behavior issues, communication skills, social skills, friendships, transition, etc.) | CM |
|  |  | - PLoP input form |  |
|  |  | - Goals input form |  |
|  |  | - SOLs for next year |  |
|  |  | - Current year grades, IEP progress, teacher input/observations (including Gen Ed), test scores, classroom performance data, other relevant information |  |
|  |  | - Services, Placement and Accommodation input form |  |
|  |  | If parent needs help understanding SOLs and grade level expectations, parent requests meeting | Parent to CM or SOL Coordinator for the county |
|  |  | If parent needs help interpreting test results, parent requests assistance |  |
|  |  | IEP team member identified to support the student, works with the student to review SOLs for next year and assist student develop input |  |
| 4 weeks prior to meeting |  | All information gathering forms completed by team members and returned | IEP Team members to CM |
|  |  | All information is incorporated into a draft | CM |
| 2 weeks prior to meeting |  | Draft of IEP shared with all IEP team members for review | CM and IEP team members |
|  |  | Ongoing communication and refinement of draft via the method selected by the team (by mail, email, in conferences, etc) | CM and IEP team members |
|  |  | Final draft sent to all IEP team members at least 2 days in advance of meeting | CM |
| Day of meeting |  | Meeting occurs; final IEP completed | IEP Team |